## Slide 1: Computing Research Project for including Digitalization in Remote working System
Module Project
Start Date : 6th August 2021
End Date : 6th September 2021
Submission Date: 8th September 2021
Module: Computing Research Project
Course: : Computing Research Project by doing digitalization for Remote Workers in Business .
Learner Name: Francis Roel L. Abarca
Enrollment ID: BDSE-0922-113
Presentation Date: 29th September 2023

## Slide 2: Contents
Document History
Version Number | Effective Date of release | Summary of Included Changes | Author
1 | 6th August 2021 | First Edition | Student Name

## Slide 3: 1. Project Definition
Project Background:
Aceadora Tech, a leading enterprise solution provider, is collaborating with Jumpstart Retail Chain, a nationwide retail giant with 750 stores, to address the challenges brought about by the post-Covid-19 remote working landscape. In response to the changing market dynamics, Jumpstart Retail Chain seeks to reshape its business model and pivot towards customer commerce. They envision the implementation of a membership program that offers exclusive deals, discounts, benefits, and more to its customers. Aceadora Tech has enthusiastically embraced this project to assist Jumpstart in this transformation.

## Slide 4: 1. Project Definition
Project Goal:
The creation and implementation of a new membership business model for the Jumpstart retail chain is the main objective of this project. By offering members special offers, discounts, and advantages, this model will increase client loyalty and spur revenue growth. The project will entail creating an extensive membership program, integrating this model into Jumpstart's current operations, starting a marketing campaign to advertise the program, and periodically evaluating its success to identify any modifications that are required. By making these adjustments, Jumpstart can improve customer satisfaction, boost income, and guarantee the long-term viability of its company operations as remote working becomes the new standard post-Covid 19.

## Slide 5: 2. Project Deliverables
Project Deliverables:
Gantt Chart

## Slide 6: 2. Project Deliverables
List of Evidences
  Screenshots of the project directory

## Slide 7: 3. Project Milestones & Tasks
Project Task ID | Project Task Description | Project Milestone ID
1 | Conduct Survey For information Gathering | 1
2 | Prepare Research Proposal template | 1
3 | Prepare Work Breakdown Structure | 2
4 | Create Gantt Chart using Project Libre | 2
5 | Compare and Evaluate Project Solution by doing Research | 3
6 | Conduct Survey for Jumpstart Opinion on Recommended Solution | 3

## Slide 8: 4. Project Environment
Technical Environment and Tools Used | List of references
Spring Tool Suite 4 | https://spring.io/tools
Visual Studio Code | https://code.visualstudio.com/download
IntelliJ IDEA Ultimate | https://www.jetbrains.com/idea/
Spring Boot | https://spring.io/projects/spring-boot
ReactJS | https://react.dev/
MySQL Server | https://dev.mysql.com/downloads/mysql/
Docker | https://www.docker.com/
Google Form | https://www.google.com/forms/about/
Microsoft Word | https://www.microsoft.com/en/microsoft-365/word?market=af
Microsoft PowerPoint | https://www.microsoft.com/en/microsoft-365/powerpoint

## Slide 9: 5. Tools
Screen capture of various tools used
  IntelliJ IDEA Ultimate (Back-End Development)

## Slide 10: 5. Tools
Screen capture of various tools used
  Visual Studio Code (Front-End Development)

## Slide 11: 5. Tools
Screen capture of various tools used
  Docker (Back-End Implementation)

## Slide 12: 5. Tools
Screen capture of various tools used
  MySQL Server (Database Server)

## Slide 13: 6. Research Proposal Template

## Slide 14: 7. Project Design
Project Flowchart:

## Slide 15: 8. Project Gantt Chart

## Slide 16: 9. Project Execution
Screen Shots of Evidences:
  Chat

## Slide 17: 9. Project Execution
Screen Shots of Evidences:
  Home

## Slide 18: 9. Project Execution
Screen Shots of Evidences:
  Register

## Slide 19: 9. Project Execution
Screen Shots of Evidences:
  Feedback

## Slide 20: 10. Milestone Feedback & Action taken
Project Milestone ID | Milestone Feedback received from Tutor / Learning Facilitator | Action Taken (Yes / No)
1 |  | Yes
 |  | Yes
 |  | Yes
2 |  | Yes
 |  | Yes
 |  | Yes
3 |  | Yes
 |  | Yes
 |  | Yes

## Slide 21: 11. Proposed Improvements
Future Recommendation:
  Utilize a faster system (Preferably one with 16 cores or more)
  Use the GPU for AI Processing
  Implement a much cleaner front-end interface.